## Sheet1
Product Backlog – Enterprise Worm Propagation & Containment
ID | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | Implement Random Fast Scanner Worm | Worm Models | As a researcher, I want to simulate a high-speed random scanning worm to evaluate rapid propagation. | Must Have | To Do | Rapid full-network infection observed in baseline model. | High-frequency random IP scanning; infection timer tracking. | Reproducible spread behavior across runs. | 3 days
2 | Implement Service-Based Worm | Worm Models | As a researcher, I want to simulate a service-targeted worm to evaluate service exploitation spread. | Must Have | To Do | Service-specific infection pattern measurable. | Target predefined vulnerable ports/services; log exploitation attempts. | Controlled, repeatable simulation. | 3 days
3 | Implement Stealth Slow Worm | Worm Models | As a researcher, I want to simulate a low-rate stealth worm to evaluate detection delay. | Must Have | To Do | Slow infection growth curve documented. | Low-frequency scanning logic; delayed infection behavior. | Accurate timing precision for detection comparison. | 3 days
4 | Model 1 – No Protection (Flat Network) | Enterprise Architectures | As a researcher, I want a baseline flat network without security. | Must Have | To Do | Total infected hosts reaches maximum in fast worm scenario. | No firewall; No IDS; No segmentation. | Represents uncontrolled enterprise topology. | 2 days
5 | Model 2 – Firewall Only | Enterprise Architectures | As a researcher, I want to evaluate perimeter firewall containment. | Must Have | To Do | External filtering applied; internal spread measurable. | Edge firewall rule implementation; logging enabled. | Minimal latency impact. | 2 days
6 | Model 3 – Firewall + IDS + IPS | Enterprise Architectures | As a researcher, I want to evaluate detection-based containment. | Must Have | To Do | Time-to-detection recorded for all worms. | Signature-based detection; alert generation. | Detection accuracy measurable. | 3 days
7 | Model 4 – Firewall + IDS + IPS + Segmentation | Enterprise Architectures | As a researcher, I want to evaluate VLAN-based lateral movement restriction. | Must Have | To Do | Cross-segment infection reduced significantly. | VLAN isolation; ACL enforcement; inter-VLAN monitoring. | Maintain network performance. | 3 days
8 | Model 5 – Novel Advanced Containment Architecture | Novelty Model (Core Contribution) | As a researcher, I want to implement a defense-in-depth architecture with quarantine and active response. | Must Have | To Do | Lowest final infection percentage achieved among all models. | Firewall; IDS/IPS; Segmentation; Dynamic isolation; Quarantine VLAN. | Scalable; measurable containment success. | 5 days
9 | Define Total Infected Hosts Metric | Evaluation Metrics | As a researcher, I want to measure final spread impact. | Must Have | To Do | Final infected host count calculated per model. | Count infected nodes at experiment end. | Statistically consistent measurement. | 2 days
10 | Measure Time to Full Infection | Evaluation Metrics | As a researcher, I want to measure spread speed. | Must Have | To Do | Time-to-full-infection recorded. | Track infection timestamps. | Accurate timing logs. | 2 days
11 | Measure Time to Detection | Evaluation Metrics | As a researcher, I want to measure IDS/IPS alert delay. | Must Have | To Do | Detection timestamp recorded per worm. | Log detection trigger events. | Precise detection latency measurement. | 2 days
12 | Measure Cross-Segment Infection | Evaluation Metrics | As a researcher, I want to evaluate segmentation strength. | Must Have | To Do | VLAN boundary crossing attempts logged. | Monitor inter-VLAN infection attempts. | Reliable segmentation logging. | 2 days
13 | Evaluate Containment Success | Evaluation Metrics | As a researcher, I want to determine if spread stopped automatically. | Must Have | To Do | Containment success flag recorded. | Monitor infection stabilization point. | Reproducible containment evaluation. | 2 days
14 | Generate Comparative Benchmark Report | Unified Benchmarking Framework | As a researcher, I want unified comparison across 5 models and 3 worms. | Must Have | To Do | Comparison graphs and ranking produced. | Aggregate metrics; visualize results. | Publication-ready formatting. | 3 days